## CCBH Project
CCBH Problematic Performance Standards Project
Level of Care | Request | Review | Next Steps- Community Care and Allegheny County OBH
Blended Service Coordination | Engagement/Re-engagement Remove the 3 attempts at face-to-face outreach - these are time consuming and non-billable. | SPA/OBH expectation. Want to see evidence of organized engagement efforts. Consider reducing the face-to-face requirement to one effort and shortening the activity window to 30 days. | Melissa Medice and Jeff Long to review updates. Coordinate with SCU Directors.
11/10/2022: County Adult OBH in agreement to reduce face to face requirement and shortening activity window to 30 days. Child & Adolescent team also reviewing. Will update current process.
1/24/23: on the SCU Director meeting agenda for 1/27/23. C&A reviewing and to report back. Language to be finalized by Feb 2023, with help of providers.
| For discharges due to non-engagement, it is not possible to obtain this information (transition and crisis/relapse plan) and should be relaxed in these circumstances. | SPA/OBH expectation. Need more information on what to be relaxed. | Melissa Medice and Jeff Long to review updates. Coordinate with SCU Directors.
11/10/22: Will review with SCU Directors to clarify scenarios and update current process expectations.
1/24/23: Review of Crisis and Relapse Plans needed at discharge. On the SCU Director meeting agenda for 1/27/23. Language to be finalized by Feb 2023, with help of providers.
| Relax the Access standards to 3 days for Urgent and 5 days for Emergent and 10 days for Routine. | Not in regulations but longstanding referral prioritization. Needs more discussion/review. | Melissa Medice and Jeff Long to have follow-up discussion. Coordinate with SCU Directors.
11/10/22: after review, will keep current expectations at this time.
| Regulation requires BSC in-person at ER presentations. | Regulation. Diversion needs to be goal and 24/7 is expectation of BSC. Would OMHSAS consider using phone, video, pandemic experience, etc. | Melissa Medice and Jeff Long to have follow-up discussion with providers. Coordinate with SCU Directors.
11/10/22: Diversion when appropriate needs to remain the goal. Allegheny DHS open to asking OMHSAS about this regulation and any current flexibility.
1/24/23: On SCU Director meeting agenda for 1/27 and plan for discussion/review to be determined.
| Crisis/ Safety plan redundancies- BSCs should be able to eliminate the task of completing a Crisis/Safety plan when one already exists. | We actually encourage a single crisis plan if possible. We would expect a copy of the plan developed by the other staff/provider and some sort of progress note/documentation showing that the plan was reviewed with the member. | Educate providers/SCU Directors about this expectation.
11/10/22: We encourage use of one crisis plan when possible. Community Care will look for copy of shared plan in record and progress note documenting crisis plan was reviewed with individual.
Providers should request TA/education from Community Care as needed.
| “Deadlines with little notice”. | Agree that when requesting data or creating deadlines that sufficient time be given to prepare quality responses. Communicate re: external timeframes for VBPs, etc. Other detail from CAP? | In Agreement with recommendation
Please provide feedback ongoing. Hope to work collaboratively on this.
| Projects timely start, data, and payment. Timeframes for projects are not clear which effects project management, outcomes, and budgeting. | Agree and Community Care continues to make improvements re: timely VBP contracts and payments. | Please provide feedback ongoing. Hope to work collaboratively on this.
Child PHP | Align with regulations. Community Care Performance Standard recommends 1:4 staffing ratio. | Review performance standards language. | Mark Hugh and Neil Glover to review and coordinate follow-up with providers.
11/10/22: Reviewing Performance Standard language and considering updates.
1/24/23: Workgroup has been convened and recommendations made to update this language. Seeking Community Care company-wide approval. Target for end of 1st quarter 2023. Will be agenda item at Allegheny PHP Provider meeting in spring 2023.
| Align with regulations. Community Care Performance Standard recommends weekly review of treatment plan. | Treatment plan to be developed in first 5 days. Review performance standards language. | Mark Hugh and Neil Glover to review and coordinate follow-up with providers.
11/10/22: Reviewing Performance Standard language and considering updates.
1/24/23: Confirmed MCO cannot be less stringent than state regs. Add Citation
| Elements of initial evaluation in Community Care Performance Standards. Decrease requirements to allow for clinicians to focus on presenting problem and clinical recommendations in lieu of long list of requirements. | Information included asked for by the state and required to determine MNG. | Community Care will confirm all elements are required.
11/10/22: Information being requested is required by the state. Will consider allowing more time to gather initial assessment information.
1/24/23: Will work collaboratively with providers to determine times. Will be agenda item at Allegheny spring PHP Provider meeting.
| Community Care Performance Standards ask for evidence of Care Coordination with PCP, ROI on file, educate PCP. | Need more information. Care coordination can be broadly defined. Review performance standards language. | Mark Hugh and Neil Glover to review and coordinate follow-up with providers.
11/10/22: Coordination is loosely defined and can include calls, correspondence, review of EHR, etc. Will clarify current expectations with providers.
1/24/23: Educate providers on expectations. Quality staff will attend PHP Provider meeting to review and at individual provider review level.
| Length of Stay should not exceed 4 weeks. CAP reporting acuity is higher, step-down levels of care are at capacity preventing follow up/continuity in care that is timely. | Although this is LOS goal, each treatment episode is individual to the member. There is flexibility in LOS if acuity is present. | Continued authorization of services based on member acuity/need.
11/10/22: Community Care will continue to extend authorization for members if acuity is present and further treatment is needed. LOS is individualized.
| Allow for program delivery based on patient need. Could expand ability for providers to provide increased intervention but cannot staff programming for 6 hours/day, 5 days/week. | Member must engage in programming at least 3hrs/day. Review PHP Provider Alert. 6/hours day no longer needed. | Mark Hugh and Neil Glover to review and coordinate follow-up with providers.
11/10/22: 6 hours per day is no longer a requirement.
1/24/23: PHP defined by at least 3 hours. Will review at spring PHP provider meeting.
| Nursing staff on site during all program hours daily. Revise to "available during program hours". | Consider waiver for this regulation. | Mark Hugh and Neil Glover to coordinate follow-up with providers.
11/10/22: Community Care and Allegheny OBH will support waiver requests for this requirement.
1/24/23: Will support individual requests for waivers at this time due to workforce challenges.
DAS | Weekly counts with shift counts for controlled medication. | Performance Standards are being updated for DAS and we will review this recommendation. Providers will need to comply with CRR requirements. | Sydell Payne and Jeff Long to coordinate follow-up with providers.
11/10/22: Updated DAS Performance Standards are being finalized. Providers will need to comply with CRR requirements.
1/24/23: PS are being finalized. Target for completion by end of 1st quarter 2023. Stakeholder workgroup agreed daily pill counts are best practice. Added counts are up to individual provider P&P. Individual meetings with DAS Providers will be held in Feb 2023 and will include this item.
| Documentation on first two shifts; documentation on overnight shift by exception only. | Need more info. What would be the exceptions for overnight documentation? Is there flexibility in the amount expected to document overnight? | Sydell Payne and Jeff Long to coordinate follow-up with providers.
11/10/22: Need to discuss further with DAS providers.
1/24/23: PS are being finalized. Target for completion by end of 1st quarter 2023. Stakeholder workgroup agreed overnight documentation is best practice. SMIs have informed this decision re: overnight programs. Individual meetings with DAS Providers will be held in Feb 2023 and will include this item.
| Coordination with BSC | Recent update to the PS indicates: "The service coordinator is expected to have weekly contact with the consumer in DAS unless other arrangements are made and agreed to by the DAS staff and the consumer, and the family/significant other as appropriate." Recent update to SD indicates: "Collaboration: DAS programs work with supportive services and natural supports to create discharge plans and community support plans. DAS programs encourage individuals to meet with their community supports at any time to address their basic needs and prepare for discharge." | Sydell Payne and Jeff Long to coordinate follow-up with providers.
11/10/22: Updated DAS Performance Standards are being finalized.
1/24/23: SD info will describe coordination with BSC.
OPMH | The member should be scheduled for their first appointment within seven calendar days of their initial request to be seen. With workforce issues, this time frame could be relaxed to 14 days. | Target measure. Evidence shows that members have higher follow through if appointment is scheduled within 7 days and are likely to follow up for subsequent appointments. | Follow-up discussion.
11/10/22: Reviewed and will keep 7-day access standard at this time. Evidence shows better follow-up and engagement if appointment is within 7 days.
| Documentation-Releases are obtained as required but it is not possible to have all support services engaged in the treatment planning process. | It would be ideal to have all services participate in the tx planning process, but it may not be realistic. Continue to obtain the releases and coordinate as needed. Can be broad- share copy, make contact, etc. | Follow-up discussion.
11/10/22: Incorporating supported into treatment planning process is valuable and can be broad- share copy of document, make contact for input, attend meeting, etc. All persons do not need to be in-person/present at the same time.
1/24/23: Quality team will continue to provide education at on-site provider reviews.
| Documentation- At discharge from IPMH, the outpatient appointment should be relaxed to 14 days and the medication appointment relaxed to 21 days. | Target measure. Impact MCO expectations. | Follow-up discussion.
11/10/22: Reviewed and will keep 7-day access standard at this time. Evidence shows better follow-up and engagement if appointment is within 7 days.
| Visits between Community Care and providers will be utilized to continue to assess a program’s success in addressing cultural needs and providing support and feedback to continue individual clinicians and overall programs growth and development. Postponement would be warranted. | This is a goal but understand timeframes may need to be extended due to workforce challenges. | Educate provider about this expectation.
11/10/22: This is process and goal is to improve over time. Community Care and OBH understand if timeframes need to be extended and let us know how we can best support this work at provider level.
1/24/23: Encourage providers to request TA a needed.
PHP | Staff ratio of 6:1 and no nurse requirement. | Review performance standards language. | Sydell Payne and Jeff Long to review and coordinate follow-up with providers.
11/10/22: Reviewing Performance Standard language and considering updates.
1/24/23: Citation. Discussion ongoing around acute vs. non-acute PHP practices. Plan for Adult PHP Provider meeting in spring and will gather feedback re: PSs language.
| Service availability of 5 days per week. | Review performance standards language. | Sydell Payne and Jeff Long to review and coordinate follow-up with providers.
11/10/22: Reviewing Performance Standard language and considering updates.
1/24/23: Discussion ongoing. Plan for Adult PHP Provider meeting in spring for feedback to incorporate re: PSs.